Purpose

A standard operating procedure has been established for developing and managing project schedules, which enables in-depth schedule analysis, timely control, and effective communication channels among project stakeholders. Additionally, it facilitates precise and realistic information reporting, monitoring of project status and progress, and the analysis of changes and their impacts.

- Scope

This procedure shall cover planning activities covering the implementation and controls required to meet the requirements of Madkour Group Projects, aspects to ensure the availability and best utilization of tools and resources to meet project requirements, and aspects to ensure the availability and best utilization of tools and resources to meet project requirements.

- Process (SIPOC)

| Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- |
| - Pre- Award Phase |  |  |  |  |  |  |  |
| Tendering Department / BD | General and Special Conditions (especially clauses related to Schedule in tender documents or planning requirements). Project scope. Tender BOQ. Available Design Drawings and technical documents. Tender Basis of Estimate (method of statement, Estimated Durations, Estimated Quantities, Productivity Rates…. Etc.) - if available | Developing the initial Tender Schedule includes: Study Scope Definition. Develop Preliminary Time frame. Create Initial Tender Time Schedule including WBS, and activities. Internal Review and Adjustments. Issue Final Tender Schedule. Create Schedule Narrative Report (if requested by client). | Planning Engineer | Final Tender Schedule (Level 2) (Narrative Report) - (if requested by client) | Tendering Department / BD | 5 D:12 D (Working days) |

| Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- |
| - Project Planning (Initiation) |  |  |  |  |  |  |  |
| Tendering Department / Business Development | - Kick off Meeting Presentation - Final Contract Document and appendices if available - BOQ | Review current planning engineers’ assignment. Assigning the Project Planner through hiring or reallocation. | Planning Manager | - Hiring Request / Transfer Request if needed - Assignment Request (by email) | HC/PM Planning Engineer | 3D |
| - Planning Manager | - Kick off Meeting Presentation - Final Contract Document and appendices (including BOQ if available) | - Create Project Work Breakdown Structure (WBS) and Activity List - Consolidate all developed plans and develop the initial baseline in accordance with the scope and the contractual requirements. - Develop the project risk register | Planning Engineer | - Initial Baseline schedule - Project Risk Register (from planning department point of view). | Project Management | 12 D |
| - Engineering Department | - Initial Engineering Plan (MDL). |  |  |  |  |  |
| - Procurement Department | - Initial Procurement Plan. |  |  |  |  |  |
| - Technical Office | - Initial Material Submittal plan (MTS) |  |  |  |  |  |
| - PM/Construction Department | - Construction Execution Plan (in case of new applied construction method). - Construction Method of Statement (or approved flowchart developed by planning department). |  |  |  |  |  |

| General Notes: | • "Initial MTS" or "Initial MDL" contains the item list without specific information to assist in creating the initial baseline schedule |  |
| --- | --- | --- |
|  | • Planning Engineer should follow up on the preparation and issuance of MTS, MDL, Execution Plan, and Method of Statement. |  |
|  | • In case of approved flowchart, it should be used as construction method and execution plan |  |
|  | • Conduct a meeting (if needed) with the project manager, construction manager, project engineer, and technical office to review and verify initial baseline. |  |
|  | • The durations are subject to change according to each project |  |

| Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- |
| - Project Planning (Detailed Baseline) |  |  |  |  |  |  |
| PMG/Cost control | - Final Priced BOQ/or cost mapping sheet - Final Contract Documents | Schedule Development: - Defining Activities weights and Weighting system assumptions in case of not applying manhour loading (represented in manhour histogram upon client request). Cost Loading (both E.V and Weighting system if required by PM). - Cost Loading (E.V if the priced BOQ or cost mapping sheet are available). Schedule Review: - The planning team leader should review the detailed schedule, relations, durations, productivity, review the critical paths, the schedule overall logic, and the cash loaded and make sure that the activity weight is matching the BOQ items price (if available). - Review the baseline schedule by Time Schedule Evaluation System (DCMA). | Project Planner Team Leader | Draft Baseline Schedule Weighting System (Activity Weights & Assumptions) | PM/Construction, Procurement, Engineering, Testing & Commissioning, TEQ | 8 D |
| Engineering | - Final MDL/Final DTS - Final MTS - Quantity Survey (QS) |  |  |  |  |  |
| Procurement | - Final Procurement Plan (including material submittal plan) |  |  |  |  |  |
| Construction | - Final Construction Execution Plan including (initial deployment plan that contains the labor and equipment). - Final Construction Method of Statement |  |  |  |  |  |
| Testing & Commissioning | - Testing Equipment Activity Guide |  |  |  |  |  |
| Planning | - Initial Baseline - Standard Sequence flow chart if available |  |  |  |  |  |
| Project Manager | Baseline Schedule R.0 including (Construction, Procurement, Engineering, Testing & Commissioning Plan) Approval | Schedule Release After reviewing with all relevant parties and ensure that time schedule covers the company obligations and rights, schedule will be released as approved baseline. Once a baseline is released it will be fixed and not allowed to be modified or changed except in the following cases: - Variation or change order by the client. Approved EOT by the client. - Approval of company top management (internal time schedule). In case of not receiving the baseline schedule approval within 5 days, the schedule will be considered as approved baseline, and the assigned planner will attach the sent email requesting approval as an approval document. | Project Planner Team Leader | - Schedule Narrative Report (if requested by client). - Project Baseline Schedule (XER-PDF). including: - Project WBS - Project Critical Path. - Project S-Curve - Project Resource Histogram (in case of resource loading not weighting system) - Progress tracking form. | Client Project Team Construction Team | 1 D |

| Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- |
| - Execution and Control |  |  |  |  |  |  |  |
| - Progress Update |  |  |  |  |  |  |  |
| Construction/ site TO | - Activity tracking sheet updated as per approved frequency (weekly or biweekly or monthly) - Daily Construction Report | Update Progress (Validation of data collected) From the updated tracking sheet by the relevant departments mentioned, and after communication with the project managers; the update of the project status will be performed using the appropriate scheduling tool: - Oracle Primavera P6. Note: Upon analysis of the update results, recommendations for recovery will be appended to the progress report, depending on the project’s situation (5% variance of project duration need to raise the flag for recovery). | Project Planner with Senior Planning Engineer | - Updated Schedule (XER-PDF). - 2 weeks look ahead. Internal or External Weekly Progress Report (Excel or PDF) contains: - Project Layout. - Project Location. - Project Organization chart. - Project information\ (Summary). - Project Overall Progress. - S-Curve. - Milestone Status. - Life Cycle Progress. - Engineering Status and Delayed Drawings and MDL KPIs. - Procurement Status and Delayed delivery and MTS KPIs. - Project trades Progress. - Area of Concern. - Financial Status (Invoices) and Payment Terms. - Progress Photos - 2 weeks lookahead schedule | Project Team including all relevant parties Client (if requested) | 2 D |
| Engineering /DC | Updated Engineering Status (MDL). |  |  |  |  |  |
| Procurement | Updated Delivery Status (MTS). |  |  |  |  |  |
| PMG/ DC/ QC | Updated NCRs and IRS Logs. |  |  |  |  |  |
| Cost Control/Project Engineer | Submitted Invoices |  |  |  |  |  |

| Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- |
| - Recovery Schedule |  |  |  |  |  |  |  |
| - Planning | - Updated project schedule. | - A meeting with all project team to assess current project status and causes of delay, if needed. - After identifying the causes of delay, planning engineer review the time schedule and take necessary action to recover the delay if applicable. - Develop a recovery schedule based on all inputs. - Review and validate the recovery schedule with the Client/project manager. | Project Planner With Team Leader | - Approved Project Recovery Schedule - MOM or Email - Action Plan including additional resources. | Client/Relevant Project Teams PM | Duration of preparing recovery schedule will vary depending on the project scope and delay events. |
| - Engineering /DC | - Updated Engineering Status (MDL). |  |  |  |  |  |
| - Procurement | - Updated Procurement & Delivery Status. (MTS) |  |  |  |  |  |
| - Construction | - Updated Tracking Sheet |  |  |  |  |  |

| Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- |
| - Revised Schedule |  |  |  |  |  |  |
| Planning | Updated project schedule. | - Assessing new modifications needed or mitigation action - After assessing the needed required modifications, the planning engineer reviews the time schedule and takes necessary action to apply the final modifications, if applicable. - Develop a revised schedule based on all inputs. - Issue the revised schedule for review and approval by the Client/project manager. | Project Planner Team Leader | Schedule Narrative Report (if requested by client). | Client Project Team Construction Team | Duration of preparing recovery schedule will vary depending on the project scope and delay events. |
| Engineering/DC | Updated Engineering Status (MDL). |  |  | Project Revised Baseline Schedule (XER-PDF) including: |  |  |
| Procurement | Updated Procurement & Delivery Status (MTS). |  |  | Project WBS |  |  |
| Construction | Construction Daily Report |  |  | Project Critical Path. |  |  |
| PMG | -Approved time extension letter (in case of time extension) -Variation Order Letter (in case of changing the project scope) with project management team recommendation to revise time schedule -Client’s request letter or email or MOM requesting revised time schedule (if initiated by the Client). |  |  | Project S-Curve. Project Resource Histogram (in case of resource loading not weighting system). |  |  |
|  |  |  |  | Progress tracking form. |  |  |

| - Delay Analysis for time Claims |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Contract | - Chronology of Project Delay Events (From Contract Department, Project Controls, and Project Management) - Project Contract. | The delay analysis process includes the following: - Planning and contracts convene meeting with procurement, Project Manager, Technical office, and Construction for analyzing events and causes, if needed. | Project Planner Team Leader | - Impacted Project Program (Time Schedule). - Delay Analysis Narrative. | - Contracts - Cost Control - Project Management | Duration of preparing a time Claims will vary depending on the project scope and delay events. |
| Planning | - Relevant baselines schedules, and updates. | - Project planner will start preparing delay analysis after receiving the required documents. |  | - Revised Baseline Schedule after claim approval |  |  |
| PMG/DC | - Delay events log including contractual correspondence documenting the project delay events. Project Documents: - Variation Orders Logs - Minutes of Meetings. - Project Income Letters/outcome Letters/Notices of Claims. - Construction Inspection Request Logs. | - Planning team leader review and issue delay analysis outputs to contract and project management departments. Duration of preparing a time Claims will vary depending on the project scope and delay events. |  |  |  |  |
| DC/Engineering | - Engineering Logs (Drawing Submittals). |  |  |  |  |  |
| DC / Procurement | - Procurement logs (Material submittals) |  |  |  |  |  |

| Source of Input | Input | Process | Done by | Output | Recipient | Duration Working day(s) |
| --- | --- | --- | --- | --- | --- | --- |
| - Project Closeout |  |  |  |  |  |  |
| PMG | - Variation Orders Logs. - MOM. - Project Income/outcome Letters. - Construction Inspection Request Logs. - Engineering /Procurement Logs (Material submittals/Drawing Submittals). | - Closeout Email. - Add any lessons learned and best practices to be applied to future projects. | Project Planner | - As Built Time Schedule - Update Lesson Learned Report - Last Weekly Update. | Planning Document Controller/ Admin | 3 D |
| Project Planner | - As Built Time Schedule - Updated Lesson Learned Report - Project Documents. | - Release Lesson Learned Report MDG-QA-MP09-FM01 Lesson Learned Report (LLR).docx - Update Lesson Learned Log MDG-QA-MP09-LOG01 LLR Log.xlsx - Archiving Project Documents. | Planning Document controller/ Admin | - Updated database | Company Database | 1 D |

- Definitions & Abbreviations

- BOQ: Bill of Quantities.

- Baseline Schedule: The frozen version of the project timeline that is approved to be a progress tracking reference.

- Critical Path: The Sequence of Network Activities that add up to the Longest Overall Duration; This Determines the Shortest Time Possible to Complete the Project.

- Claim event: any contractual event that entitles MADKOUR to time or cost impact throughout the project cycle.

- EDL: Engineering Drawings List.

- EOT: An extension of time claim is a request for a change in the scheduled completion date due to a delay that is not the contractor's fault. The delay could be caused by natural events, owner delays, or other unexpected occurrences.

- MTS: Material Tracking Sheet.

- MDL: Master Document list.

- Narrative Report: Is a report that Provide Summary of project scope, Explain the Plan for Construction, Show How the Schedule Meets Contract Requirements; summarize the critical path and discuss potential problems.

- PMG: Project Management Department.

- PM: Project Manager.

- Project Master Schedule: This is an early communication tool among stakeholders that shows the major deliverables, key milestones, and a summary of work breakdown structure activities. Simply put, a master schedule is prepared for tracking the project at a summary level.

- S-Curve: A graph describes, visualizes, and predicts a business’ performance progressively over time.

- Schedule Level 1: Is typically a one-page bar-chart and milestone list that outlines, in broad form, the project's objectives, significant milestones, and phase relationships.

- Schedule Level 2: It depicts the overall project broken down into its major components by area and is used for higher-level management reporting. Frequently developed by the 'client' as part of its commitment planning for the project and then maintained by the contractor.

- Schedule Level 3: Contain all project scopes and are derived from key project execution stakeholder information (equipment suppliers, contractors, construction experts, etc.).

- Variation Order: Any Request That Changes Significant Changes That Affect the Project; Changes to Several Project Areas, Including Requests to Expand or Reduce the Scope of the Project.

- WBS: Work Breakdown Structure.

- KPI: Key Performance Indicator.

- Pre- Award Phase: the phase before a contract is awarded by the client or project owner. This phase involves a series of critical activities related to preparing, submitting, and potentially winning a bid or tender for a project. This process is activated only if required by tendering or business development department.

- Initial Phase: An early project schedule created after contract award, reflecting the preliminary plan based on available information. It typically includes major milestones, key deliverables, and detailed activity breakdowns, it serves as a timeline reference for the project (it includes durations only without weighing system, resources, or cost loading)

- Planning Phase: is the fully developed, resource- and cost-loaded schedule that reflects the contractor’s comprehensive execution plan. It includes all project activities, logical sequencing, durations, resource assignments, and progress measurement criteria, and is used as the official tool for tracking and controlling project performance.

- MTS: It includes material supply items with all details (quantity, durations, dependencies, … etc.)

- MDL: It includes design drawings, calculation notes, cable lists, FAT, …. Etc.

- Recovery Schedule: A recovery schedule refers to actions and steps that must be performed to get a project back on track once it has been delayed (5% variance of project duration). The recovery schedule is issued after Planning Manager approval, either at the client’s or Project Manager request. Not every delay requires a recovery schedule—only those with a significant impact on the running and feasible project.

- Revised Schedule: A revised schedule refers to modified time schedule to represent new baseline with new methodology, scope, or finish date. It is produced in one of the following cases: (1) Approved extension of time; (2) Variation Order; and (3) Client Request.

- Delay Analysis for time Claims is the process of analyzing the reasons of delay to request extension of time claim in case of compensable delays affecting the approved baseline.

- Project Closeout: Project closeout, from a planning perspective, is the final phase in which all planning responsibilities are concluded, documentation is finalized, and performance records are closed. The responsibility of planning activities comes to an end once the project reaches 90% progress.

- Responsibilities:

Planning and controlling Department:

- Define project scope, activities, dependencies, and resource requirements (manpower, materials, equipment).Develop Project plans/schedules (tender, initial/detailed baseline, updates, and recovery/revised).

- Track actual progress against the baseline schedule, monitor and analyze project performance using qualitative and quantitative tools Analyze performance variances and conduct delay analyses to identify root causes.

- Manage scope changes and assess their impact on the schedule.

- Continuously monitor risks and issue formal warnings for any serious deviations threatening the plan's execution.

- Recommend and implement action plans to improve effectiveness and achieve key project’s milestones.

- Develop the Progress Report (Internal/External) communicating project status, key issues, risks, and performance forecasts.

- Develop Standard process flowcharts according to project type, if needed, to define workflow sequence.

- Update Lesson Learned Log and ensured proper archiving of all project documents Develop, implement, and continuously optimize departmental planning and scheduling standards to enhance process efficiency and performance.

- Planning Manager:

- Report directly to operation director, providing strategic insights and portfolio performance updates.

- Create and implement enhancements to the strategies planning business process that team members will use throughout department processes and interaction with other departments.

- Managing the development of the official department planning manual which standardizes all planning and schedule management plans, interface management plans, planning, and scheduling principles, baseline and change management plans and contractor’s schedule acceptance process.

- Manage the department's full audit cycle, from preparation to response, for both internal and external assessments of planning standards and data integrity Lead the entire department's planning team, including all roles..

- Manage departmental resource planning, including hiring, training, and professional development to build team capability.

- Assign project planners and review team workloads to ensure optimal utilization and project coverage.

- Attend the formal handover from Proposals and Estimating at the start of the project in accordance with Corporate Procedures.

- Establish and define any job-oriented planning procedures and identify the level of resources required to operate them for each project.

- Assign work to professionals and ensure that they receive appropriate training.

- Supervise the activities of planning teams both in their productivity and the technical adequacy of their output.

- Managing the establishment of project KPIs and success measurement protocol.

- Assign project planners and review team workloads to ensure optimal utilization and project coverage.

- Manage departmental resource planning, including hiring, training, and professional development to build team capability.

- Define team objectives, individual responsibilities, and performance targets aligned with departmental goals. Prepare progress monitoring tools for the management and monitoring of overall portfolio operations.

- Establish and agree on the level and frequency of reporting required for each sector and project

- Review schedule trends to identify problem areas and recommend corrective action to management.

- Providing counsel and Act as the department’s primary representative in cross-functional and client meetings.

- Plan required resources for the department to cover all running and incoming projects.

- Review the baseline schedule by Time Schedule Evaluation System.

- Review and validate the recovery schedule with the Client/project manager.

Planning Team Leader:

- Report directly to planning manager.

- Lead and mentor project assigned planning team.

- Ensure the quality and accuracy of integrated schedules through direct supervision of their preparation and updates Participate in claims analysis and negotiations

- Support the implementation of the department business process policies and procedures.

- Monitor, control, and take ownership of the report on the progress of the work in comparison with the baseline budget and schedule and report on any deviation, while ensuring the accuracy of the data.

- Accumulates and access historical data, such as performance experience, for use in maintaining a realistic basis for future planning and forecasting.

- Provide guidance and specialized assistance to project teams in the solving of project planning issues.

- Report schedule status to all levels of project and department management as well as to the client.

- Attend meetings (both internally and externally) and discuss/present schedule/progress-related matters.

- Proactively highlight any project risks or issues to project managers concerned to ensure the project is not adversely impacted and ensure the delivery of projects is compliant with standards.

- Collaborate effectively across the organization to ensure the project delivery.

- Interface with the project team to develop project forecasts and analyze the project.

- Support in Defining Activities weights and Weighting system assumption and Cost Loading (E.V if the cost data (priced BOQ or Cost mapping sheet).

- Review the detailed schedule for relations, durations, productivity, critical paths validity, the schedule overall logic, and make sure that the activity weight matches the BOQ items price.

- Coordinate the department's participation in audits, ensuring the team provides accurate data and required documentation.

Sr. Planning Engineer:

- Report Directly to the planning team leader.

- Act as the technical authority for schedule development and analysis on assigned projects under the supervision of the team leader.

- Mentor both Planning Engineers and juniors and review their work for quality assurance.

- Ensure the correct scope of work is accurately reflected in all assigned schedules.

- Develop a realistic, detailed, and resource-loaded project schedule, including the complete WBS and activity list, by integrating data from all project departments.

- Prepare periodic progress reports identifying project areas of concerns, create critical action reports, and maintain a log of all project events, Supervise project data collection and regularly update project schedule and make sure the progress status is clear and known to all project parties.

- Maintain events recorded (Internally or externally) and report directly to planning team leader and project manager.

- Lead weekly Progress meetings with cross functional project teams (contracts, Project Manager, Technical office, and the Construction managers) to discuss project status.

- Create/Support in the development of Tender Time Schedules and create the project risk register. Conduct internal schedule reviews and implement necessary adjustments to maintain accuracy and alignment with project objectives.

- Support internal and external schedule audits by providing accurate data and necessary clarifications.

Site Planning Engineer:

- Report directly to senior planning engineer.

- Execute all tasks in accordance with standard project planning and scheduling procedures.

- Support Senior Engineers in the development, updates, and approval cycles of project schedules.

- Preparation of Trackers / Logs to monitor critical issues during the Design and Construction stages of the Project.

- Collect and verify daily/weekly progress data directly from the construction site.

- Keep a proper, detailed record of all project events, delays, and site conditions.

- Develop and issue short-term look-ahead schedules (e.g., 2–4-week plans) to guide the execution team.

- Monitor adherence to the look-ahead schedule and follow up on data collection.

- Attend progress meetings and report on schedule status as required.

- Measurement (KPIs):

- Ensure that 100% of the requested tender schedules are created in accordance with the clients' acceptable criteria and within the time range given for the process.

- Ensure 100% of the company’s new projects are covered by an approved time scheduled (internal and external) within the process's specified time frame.

- Ensure that all ongoing projects with less than 90% completion are monitored and reported on a weekly basis.

- Ensure 100% of all Projects milestones and any schedule variance are properly monitored and reported.

- Ensure 100% of all project change requests are documented, monitored, and assessed.

- Ensure 100% of company claims are covered with proper delay analysis and narrative.

- Ensure that all project data and lessons learned are documented.

BD: Business Development Department

BOQ: Bill of Quantities

General Notes:

- This process (A) is activated only if required by S&T or business development department.

- Scope statement and narrative report are delivered upon request.

WBS: Work Breakdown Structure.

MDL: Master Document List It includes material supply items with all details (quantity, durations, dependencies, … etc.)

MTS: Master Tracking Sheet it includes design drawings, calculation notes, cable lists, FAT, …. Etc.

PMG: Project Management

TEQ: Tools and equipment

DTS: Document Tracking Sheet

EOT: Extension of Time

XER: Primavera File Extension

WBS: Work breakdown structure.

•  The durations are subject to change according to each project

TO: Technical Office

PMG: Project management

DC: Document control

QC: Quality Control

NCR: Notice of Change Request

IRS: Inspection Request

MOM: Minutes of Meeting