cPurpose

This Process has been developed to set a standard operating procedure for managing all Technical Office activities to ensure proper interfaces with all project departments.

# Scope

This Procedure is applicable for all MADKOUR Projects.

# Process (SIPOC)

| S. | Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Project Initiation |  |  |  |  |  |  |  |
| ## Project Initiation |  |  |  |  |  |  |  |
|  | PM | - Tender Handover Meeting Notification - Project Description and Scope of Work. - Signed Tender / Contract Documents - Final Tender BOQs - Project Technical Specifications - Vendor Offers (Drawings, Calculations and Guarantee Schedules). - Project Time schedule | Process Title: Tender Handover Process: - Attending the Tender Handover Meeting - Receiving the Input Documents by E-mail. - Assign the Project’s TO Team | TO Manager | Assigning Project’s TO Team via email | To: PM CC: TO Team | 1 Day |
|  | PM | Kick Off Meeting Invitation | - Attending kick off meeting. - Introduce team. - Receive project communication plan. | TO Manager | TO Project Organization | Project Involved Departments | 1 Day |

|  | Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Create MTS |  |  |  |  |  |  |  |
|  | PM PEL | - Project Description and Scope of Work. - Signed Tender / Contract Documents - Final Tender BOQs - Project Technical Specifications - Vendor Offers (Drawings, Calculations and Guarantee Schedules). - Project Time schedule -MDL (MDP-TO-BP01-LOG02) Project execution plan | - Create Initial MTS | Assigned TO Engineer | - Initial MTS (MDP-TO-BP01-LOG01) | PM/Planning/PRC | 5 Days |
|  | PEL TO Engineer | - MDL (MDP-TO-BP01-LOG02) - Initial MTS (MDP-TO-BP01-LOG01) | - Delivering and confirming the dates for the MTS - Attending workshop meetings with the PM, Planning and Proc. Dep. to agree and finalize the MTS. In case the dates do not match with the project schedule, the PM shall discuss the dates with Proc. and Planner and send the updated Date to T.O. | TO Engineer | Updated MTS (MDP-TO-BP01-LOG01) | - PM - Planning - Proc. | 1 Day |

|  | Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Preparing QRs, PRs. Technical Evaluations for Vendor Offers and Manufacturing release process |  |  |  |  |  |  |  |  |
|  | TO | - Signed Contract Technical Specifications and key drawings. - International Standards. - Reference manufacturer/ Utility/ Designer standards. - Common Practice. - Previous Projects. - Vendor Documents (Drawings, Calculations and Guarantee Schedules). - Geotechnical Reports - Working Instructions | - Create QRs for the and submitting it to the Proc. Dep. to start obtaining offers from the vendors. | TO Engineer | Technical QRs (MDP-TO-BP01-FM02) | Proc. Dep. | Based on the MTS dates |
| - 6 | Proc. Dep. | - Technical Offers from Proc. Dep. | - Receive & review the Technical Offer and determine any comments. | Assigned Engineer for each package. | Technical comments on the Vendor Offers | TO | Upon receiving from Vendors |
| - 7 | Assigned Engineer for each package | - Technical comments on the Vendor Offers | - In case of systems & equipment, TO shall submit and follow up the technical comments on the Vendor offers directly to the Vendors. - For others, the technical comments will be sent to the Procurement Team. | TO | Technical comments for the Vendor Offer | To: Vendors CC: PRC, PM | Directly after the previous step |
| - 8 | TO Engineer | - Final Technical Evaluation for the Vendors | - Submitting the Final Technical Evaluation for each Vendor indicating the final status of the offer (Accepted / Rejected) and the Technical Compliance Sheet. | TO Engineer | Final Technical Evaluation for the Vendors Offers | To: PRC CC: PM | As per Project Schedule |
| - 9 | TO Engineer | - Final Technical Offers | - Confirming the selected vendors with the Proc. Dep. and PM. - Submitting the final Technical Offers (Material Submittal) to DC in order to transfer it to Consultant/Client for Approval. - The T.O shall follow up the consultant feedback and in case the material approved TO shall initiate the PR cycle. | TO Engineer | final Technical Offers (Material Submittal) | DC | As per Project Schedule |
| - 10 | DC Cost control MC | - approved Technical Offers - Task Number - Expenditure type - Material codes list | - The TO shall request task and expenditure mapping sheet from cost control team. - in case of new item (not coded) Material Inventory Control (MDP-MC-BP05) clause 3.1.1 item code shall be implemented - Create the PR on the system. | TO Engineer | ERP PR | PRC Process PM | As per Project Schedule |
|  | Proc. Dep. | - Request for important technical notes by email | Type the important technical notes which shall be mentioned in the PO. | TO | Technical important notes on PO by email | Proc. Dep./PM | As per Project Schedule |
| - 11 | Proc. Dep. | - Draft PO Documents on Oracle ERP | Review and approve the Draft PO Documents on the Oracle ERP. | TO Engineer | Approved / Reject PO | Proc. Dep./PM | As per Project Schedule |
|  | TO Engineer | - Final Approved Technical Documents | - Review and ensure all required documents are available and approved. - Sign the Manufacture Release Decision as either Yes or No. | TO Engineer PM | Approved Manufacture Release | TO | 1 Day |

|  | Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## PM and Construction Review Cycle |  |  |  |  |  |  |  |
|  | PEL | Engineering documents | - Review the received documents from Engineering Department - Submit to the PM / Construction team and obtaining their comments on the Engineering Documents. - In case of any change requested by any department which conflicts with contract specification due to financial reason or agreement with the client, a change Request shall be signed by the Sector Director before initiating any change. - In case the reviewing process exceeded the stated duration without receiving comments, the TO will proceed with issuing the documents to the Client/Consultant. | TO engineer | Commented Verified Documents with “Comments Sheet”. Submitting Comments to the Vendor. change Requests | ENG SD | 2 Days |

| ## Submission to Consultant / Client |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | PEL | Official submission | - Submit the Official submission to the DC Department with Transmittal (MDP-TO-BP01-FM03) Table containing document name, number, and revision. | TO Engineer | - Official Submission | DC | 1 Day |
|  | DC | Official submittal | - TO shall confirm that the Official revisions are printed by DC according to the written paper size of each document. - Sign the Transmittal (MDP-TO-BP01-FM03) cover prepared by the DC. - TO shall confirm that the Official submissions was submitted to the Consultants / Client through the DC Department via the official communication channels (E-mails, Hardcopy, etc…). - The T.O shall follow up the consultant feedback. TO shall confirm that all the submitted documents are included in the Transmittals cover. | TO Engineer | - Official submittal - Transmittals (MDP-TO-BP01-FM03) | Consultant / client |  |

|  | Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Preparing Shop Drawings |  |  |  |  |  |  |  |
|  | TO/DC | Consultant/ Client Approval of the Official Revision | - Prepare the shop drawings in case the design drawings were either approved / approved with comments from the Consultant / Client. - Send the shop drawing to DC to obtain consultant / client approval if required then forward the approved shop drawing to Site DC / TO. - In case the approval of consultant / client is not required, the shop drawing shall be delivered direct to Site DC / TO. | TO | Approved Shop Drawings | DC Site DC/ TO | As per MDL durations |
| ## Release IFC Drawings |  |  |  |  |  |  |  |
|  | TO | Approved Design drawing | - Stamp and release the IFC drawings to the Site DC/TO after obtaining the approvals from Consultant/ Client - In case of the drawing approved with comment, TO shall get confirmation from ENG via email to stamp & release IFC drawing to Site DC/ TO. - In case of exceptional IFC drawings, PM shall obtain Sector Director approval on exception memo. | TO Engineer | IFC Drawings | Site DC /TO | As per MDL durations |

|  | Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## ITP and Attending FAT |  |  |  |  |  |  |  |  |
|  | Vendor/ QC/ T&C / PM | ITP MDP-QC-BP01-FM01 | - Reviewing collected comments from QC department on the ITP and get the required approval from consultant. | TO | Commented ITP (MDP-QC-BP01-FM01) | Vendor Client Consultant | As per MDL |
|  | Vendors | FAT (MDP-QC-BP01-FM09) Notification | - TO Manager shall assign the qualified Engineer to attend the FAT according to the FAT matrix if needed. | Assigned Engineer | Attending the FAT | DC | As per project schedule |

| S. | Source of Input | Input | Process | Done by | Output | Recipient | Duration |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ## Project Execution |  |  |  |  |  |  |  |  |
| ## Material Tracking and Control |  |  |  |  |  |  |  |  |
|  | TO Engineering Lead PM | PR Approved shop drawing-IFC drawings MTS (MDP-TO-BP01-LOG01) BOQ Project Execution Plan | Create QS sheet and compare it with client BOQ and Issue variation request if variance detected. In case of any required update - Action Plan shall be created. In case of no update required -Prepare detailed Qs. -Develop Material Control Report MCR. -Issue site material PR (Complementary materials) | Site TO Engineer | Variation Request (Oracle ERP) Action Plan Detailed QS sheets MCR (MDP-TO-BP01-FM08) PR (Oracle ERP) | PM PM DC/MC/CT PRC /PM |  | 5 Days |

| S. | Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Subcontractor Request |  |  |  |  |  |  |  |
|  | PM, CM, Planner, Cost Control | Execution Methodology BOQ IFC Drawings / Exception request task number, expenditure type -Breakdown Analysis | - Review the work breakdown structure (WBS) and check the assigned resources. - Issue subcontractor requests for planned activities. - Cleary review (type of contract, scope, quantity, unit of measurement, task number, expenditure type). Ref. to (Proc. Approval groups MDP-PRC-BP01-ANX11) * In case SCR return from procurement with comments TO shall resubmit SCR after cover procurement comments. | TO Engineer | Subcontractor request on ERP system (SCR) (service PR) | Cost Control Engineer PM PRC | 3 Days |
|  | PRC Requester PM | Draft Subcontractor Contract Variation Order Approved SVO Draft | - Review the scope of work; the quantities and units of measurement mentioned match the ones created. - Review that the payment breakdown percentage is clearly defined for any lump-sum items. Ref. to (Proc. Approval groups MDP-PRC-BP01-ANX11) - In case of any Subcontract variation - Type of changes: - Quantity Change/ Omission - Price Change - New Item - Cycle Approval take Place on System - Claims - TO engineer shall create subcontract variation Request (SVR draft) through ERP. - prepare final SVO after cycle approval (Contract Amendment) and send it to subcontractor. | TO Engineer PRC | Reviewed Subcontractor contract SVR on ERP Final SVO (Contract Amendment) | PRC PM PM Subcontractor | 1 Days |

| S. | Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Material Availability Checking Cycle |  |  |  |  |  |  |  |
|  | Planner PM/PE | 2 Weeks lookahead Schedule | - Review shop drawings, IFC drawings, and MCR to check the availability of material. - Review implemented SCR to check the availability of resources | TO Engineer | Action plan |  | 3 Days |
|  |  |  | In case of any missing item - TO engineer shall expedite drawings approval, PO, SCR process and develop action plan. |  |  | PM/Planner/PRC/PEL |  |

| S. | Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Internal Material Inspection Request Technical Cycle |  |  |  |  |  |  |  |
|  | PM | Delivery notification | - Review technical description. - Fulfill IMIR technical details | TO Engineer | Signed IMIR (MDP-QC-BP01-FM02) | QC | 1 Day |
|  | QC | FAT |  |  |  |  |  |
|  | MC | IMIR (MDP-QC-BP01-FM02) |  |  |  |  |  |
|  | PRC | PO Packing list |  |  |  |  |  |

| S. | Source of Input |  |  | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ## Material Receiving Voucher Cycle |  |  |  |  |  |  |  |  |  |
|  | MC |  |  | MRV (MDP-MC-DP01-FM06) | - Fulfill required data in MRV request (Storage technical consideration - storage duration) Review MRV & sign. | TO Engineer/MC/QC Engineer | Signed MRV (MDP-MC-DP01-FM06) | MC/QC | 1 Day |
|  | Planner |  |  | Delivery Note |  |  |  |  |  |
|  | QC |  |  | Approved IMIR (MDP-QC-BP01-FM02) approval |  |  |  |  |  |

| S. | Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## IMR and SCIMR approval cycle |  |  |  |  |  |  |  |
|  | Construction Team Subcontractor Cost Control PM | IMR (MDP-MC-DP01-FM13) SCIMR (MDP-MC-DP01-FM18) Task Mapping sheet (at the project kick-off \ if updated during progress) Exception Request (if required) | - Technical Office shall determine the required quantities on IMR/SCIMR based on the approved shop drawings, IFC and quantities survey and the area of work as per the construction plan. - Review and approve construction internal material - request and Subcontractor internal material request on ERP (if available) according to material control report, (IR-IIR), shop drawing and QS. - Task number shall be fulfilled by TO engineer. - In case of released quantities without IRs /IIRs exceed ratio 5%, exception material request must be obtained (signed by project manager – related construction sector manager) to release material. - In case of release material to subcontractor without subcontract agreement, exception material request shall be approved by Sector Director. - Note: The Site Manager may be delegated to sign the exception request for one-time, provided that he must get the approved exception request signed by project manager – related construction sector manager within one working day | TO Engineer SM | Updated MCR (MDP-TO-BP01-FM08) Approved IMR (MDP-MC-DP01-FM13) Approved SCIMR (MDP-MC-DP01-FM18) Exception request (MDP-MC-DP01-FM43) | CT TO PM/SD | 2 Days |

| S. | Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## MSR and SSR approval cycle |  |  |  |  |  |  |  |
|  | Construction Team | MSR (MDG-MC-DP01-FM07) SSR (MDG-MC-DP01-FM27) | - Approve material site return. - Approve scrap site return. | TO Engineer | Approved SSR (MDG-MC-DP01-FM27) / MSR/ Updated MCR (MDP-TO-BP01-FM08) | CT/MC | 1 Day |

| S. | Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Material Report |  |  |  |  |  |  |  |
|  | MC | Monthly Material Report (MDG-MC-DP01-TM06) | - Review monthly material report and issue sub inventory transfer request if needed | TO Engineer | Updated material report (MDG-MC-DP01-TM06) Sub inventory transfer request ERP | MC, PM | 1days |

| S. | Source of Input | Input | - Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Material Aging Report |  |  |  |  |  |  |  |
|  | MC Planning | Material Aging report Updated schedule | - Review Material Aging report and focus our attention on (work on progress) sub inventory. - In case of material still working material storage extension request shall be issued quarterly. For CM/SM approval - In case of martial no longer used Issue sub inventory transfer request to allocate material in excess sub inventory | TO Engineer | material storage extension requests ERP Updated material report (MDG-MC-DP01-TM06) Sub inventory transfer request ERP | MC, PM | 2days |

| S. | Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Quantities Reviewing Cycle |  |  |  |  |  |  |  |
|  | QC Engineer CM | IIR (MDP-QC-BP01-FM04) / IR (MDP-QC-BP01-FM05) | - Review executed quantities with estimated quantities in QS and Shop drawings. - In Case the executed quantities are within estimated quantities MCR shall be updated. - In case of there is a variance detected. Verification report shall be issued and approved by PM and related construction sector manager | TO Engineer | Updated MCR (MDP-TO-BP01-FM08) Verification Report | PM/QC/DC/MC CM / PM | 3 Day |
|  | PM - construction sector Manager |  | In case of the executed quantity proved by Verification report, Subcontractor variation request will be created. |  | Subcontract Variation Request (SVR) (Oracle EPR) /Client Variation Request | PM/ENG/QC/DC | 1 Day |

| S. | Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Work Performed Quantity Statement |  |  |  |  |  |  |  |
|  | Cost Control Construction Team QC Engineer PM/PE | Work performed sheet Signed Subcontractor progress report. IIR (MDP-QC-BP01-FM04) IR (MDP-QC-BP01-FM05) Approved Clint Invoice | - Prepare Monthly Work Performed Quantities indicating performed quantities with an IR, IIR and other executed quantities without requests. | TO Engineer | Work performed quantity statement | Cost control engineer/PM | 3days |

| S. | Source of Input | Input | Process | Done by | Output | Recipient | Duration Working day(s) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Construction Field Change Request |  |  |  |  |  |  |  |
|  | Construction Manager/ CT | FCR (MDP-TO-BP01-FM04) | - In case of modification requested by CT on design drawings, TO engineer shall review field change request. - If field change request is technically accepted TO engineer shall send it to Design engineer for drawing update. | TO Engineer | Accepted FCR (MDP-TO-BP01-FM04) | Eng. project lead/DC CT/PM | 2 Days |

| S. | Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Client Invoice |  |  |  |  |  |  |  |  |
|  | Project Manager | Email to request initiate client invoice |  |  |  |  |  |
|  | - Construction - QC | - Site Progress report - Approved IRs (MDP-QC-BP01FM05) - MIRs (MDP-QC-BP01-FM03) | - Receive progress data & quality documents - prepare the client invoice and submit it for PM for review | Site Technical Office | Client Invoice draft | PM | 3: 6 Working days |
|  | Site Technical Office | Client Invoice draft | - Review with AR & provide modifications/feedback if any | PM | Client Invoice reviewed draft | Account receivable | 2 working days |
|  | Account receivable | Reviewed draft client invoice | - Finalize AR comments & submit invoice to client consultant | PM | Finalized Client Invoice | Site Technical Office | 2 working days |
|  | Site Technical Office | Finalized Invoice | - Review and approval of the invoice. | Client Consultant | Signed Client Invoice | HQ-TO Engineer | 2 working days |
|  | Client Consultant | Approved / Signed Invoice | - Receive the Approved client invoice and submit it on ERP System. | HQ- Technical Office | Client Invoice Pending on ERP | Project Manager | 1 working day |
|  | HQ- Technical Office | Client Invoice Pending on ERP | - ERP Client Invoice approvals. | - TO manager - AR - PM Cost control | Approved Client Invoice on ERP | - HQ- Technical Office | 2 working day |
|  | AR | Final approved client Invoice | - The AR shall follow invoice collection. | AR | Issued Cheque | AR | Depends on the client’s process timeline |

| S. | Source of Input | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Breakdown Analysis |  |  |  |  |  |  |  |
|  | CM PM Tender team | Lump-sum items initial break down weighting analysis | - Review and update the breakdown statement for all lumpsum items and make sure that the analysis clearly covers all item details and that the document rectifies all needed data. - Send Breakdown weighting analysis to PM, CM, SM for approval. | TO Engineer | Breakdown analysis for approval | PM/CM/SM | 3 Days |
|  | PM | Exception letter for any missing document. | In case of any Exception required PM Shall submit / sign Exception letter to be reviewed by TO engineer and check that rectify all needed item and signs. | PM | Exception letter | TO Engineer | 1Day |

| S. | Source of Input |  | Input | Process | Done by | Output | Recipient | Duration |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ## subcontractor invoice. |  |  |  |  |  |  |  |  |
|  | CM QC MC SM/Site accountant / HC / HSE / FAC/ TEQ PM |  | Signed subcontractor execution statement. Subcontractor contract Approved IRs (MDP-QC-BP01-FM05). IIR (MDP-QC-BP01-FM04) SCIMR (MDP-MC-DP01-FM18) Deductions reports (MDP-HC-DP08-FM03) Custodies /advance payment Exception form approved item breakdown weighting analysis. | - Review and issue subcontractor draft invoice for PM approval. In case of any Exception required - TO engineer shall receive a signed exception form from PM to proceed. | TO Engineer | Drafted Subcontractor invoice (MDP-TO-BP01-FM01) | PM/CM/SM | 2-3 Days |
|  | TO Engineer |  | Subcontractor Draft invoice | - Review and sign Subcontractor invoice and send it to be reviewed and signed. | PM/CM/SM/ Subcontractor | Signed and stamped Subcontractor invoice | TO Engineer | 1Day |
|  | PM/ CM/ SM |  | Signed and stamped invoice. Signed item breakdown weighting analysis. signed exception letter in case of any missing document. | - Review all collected data and invoice attachments. - Issue subcontractor invoice on ERP system. | TO Engineer | Pending Subcontractor invoice on ERP system | PM/ TO Engineer | 1Day |
|  | TO Engineer |  | Pending Subcontractor invoice on ERP system | - Review the initiated invoice prepared and rectify all needed attachment. | TO Manager / Assigned HQ TO Engineer | Approved Subcontractor invoice on ERP system | Cost control engineer/ PM / Finance | 1 Day |
|  | PM QC/CM/SM/DC TO Engineer MC |  | Signed subcontractor execution statement. SC Site Clearance Signed item breakdown analysis. Deductions reports Custodies / loans Approved IRs / IIRs / TOAC32 Approved QS Subcontractor Invoices SCIMRs 33/ SCMSRs / SSRs | - Prepare / update Final Subcontractor material report. - T.O Engineer shall fulfill the contracted Q.S & the invoices Q.S. - The MC shall fulfill the SCIMRs / SCMSRs / SSRs. - The Q.C engineer & CM fulfill the IRs / IIRs. | TO Engineer MC QC/CM | Updated Final Subcontractor material report (Subcontractor Final Q.S Sheet). | Cost control engineer/PM | 2 Days |
|  |  | PM QC/CM/SM TO Engineer MC PM TO Engineer PM | - - Signed subcontractor execution statement. - report. - Subcontractor Site Clearance - Signed item breakdown analysis. -Deductions reports -Custodies / loans -Approved IRs / IIR Or TOAC -Approved QS -SCIMR (MDP-MC-DP01-FM18) SFIR (MDP-TO-BP01-FM09) -Pending subcontractor final invoice on ERP -Signed and stamped Subcontractor Final Invoice. -TOAC or exceptional approval of POD. | - in case the subcontractor scope completed and issued TOAC, TO Eng. should prepare subcontractor final invoice. In case the subcontractor scope completed without any opened dependent items and without issuing TOAC, TO Engineer shall request an - exceptional approval of POD (SFIR)to proceed with Subcontractor final invoice. - issue and Review subcontractor final invoice. Submit subcontractor final invoice on ERP system. - Review all collected data and invoice attachments. Review and approve final subcontractor invoice on ERP system. | TO Engineer TO Manager / Assigned HQ TO Engineer | Draft Subcontractor Final Invoice. Pending subcontractor final invoice on ERP | PM HQ-TO Engineer / TO Manager | 5 Days |
|  |  |  |  |  |  | Approved final Subcontractor invoice on ERP system | Cost control engineer/PM/ finance |  |
|  |  | - PM | - Approved final Subcontractor invoice on ERP system. - Subcontractor Retention release request - TOAC | - Review retention release request sent by PM, and it must contain (project name-contract no.-TOAC) or accordance with the contract terms & conditions. - Issue retention release on ERP system. | TO Engineer | Approved retention release request | Finance/PM | 2 Days |

| Sn | Source of Input | Input | Process | Done by | Output | Recipient | Duration Working day(s) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Project Close-out |  |  |  |  |  |  |  |
| 1 | CT QC | Red marked drawings | - Prepare the as built drawings. | TO Engineer | As built drawings | Client/ Consultant/ DC | Ongoing process |
| 2 | PM | TOAC | - Prepare client final invoices. | TO Engineer | Client Final Invoices | PM/DC | 7 Days |
| 3 | All Involved Departments | Lessons Learned (MDG-QA-MP09-FM01) | - Collect technical lessons learned from all project departments. | TO Engineer | Technical Lessons Learned (MDG-QA-MP09-FM01) | All Functional Departments | 7 Days - Days |
| 4 |  |  | - Update lessons learned log and archive all project documents. | DC |  |  |  |

# Deviation:

- Deviations than any of the Technical Office Business Process requirements shall pre-approved using the Request for process Exception Form.

- Before Management approval, TO Evaluation for all technical risks shall be added.

# Duration

- The Mentioned process durations maybe changed due to workload and priorities.

# Responsibilities:

- Project Manager:

  - Notify the Technical office about new projects.

  - Invite the technical office to attend project Kickoff meeting.

  - Initiate client invoice issuance request via email to the Technical Office.

  - Submit the technical Package.

  - Approve MTS and Subcontract List.

  - Attend workshop meetings to set material and document schedule.

  - Confirming the shortlisted vendors

  - Review and put his comments on the documents from Engineering Department

  - Approve on variation request.

  - Submit and sign on exception letter.

  - Approve on investigation report.

  - Provide Project Execution Plan.

  - Approve PRs/SCRs/ITRs.

  - Approve Subcontractor’s and Client invoices.

  - Send Required approved documents for tender hand over to technical office manager.

  - In case the dates do not match with the project schedule, the PM shall discuss the dates with Proc. and Planner and send the updated Date to T.O.

  - In case of exceptional IFC drawings, PM shall obtain Sector Director approval on exception memo.

  - Approve Inspection and testing plan.

  - Receive detailed QS sheets and action Plan In case of any required update in execution plan.

  - Send Approved SVO Draft to Technical office.

  - Review and approve action plan In case of any missing item in shop drawings, IFC drawings and MCR reviewing cycle.

  - Send Material Delivery notification and ready to Internal Material Inspection.

  - Receive, review and approve exception material request in case of released quantities without IRs /IIRs exceed ratio 5%.

  - Review and approve Sub inventory transfer request.

  - Approve MCR, Verification Report and Subcontract Variation Request.

  - Review and approve Overtime sheet.

  - Perform final internal review and approval of the client invoice after Cost Control clearance.

  - Officially submit the approved invoice to the client technical department and notify the Finance/AR department of delivery.

  - Review the monthly invoice status report received from the AR department for cash flow monitoring.

  - Send TOAC to technical office engineer and receive Client Final Invoices.

  - Apply Finance/AR modifications and comments to the draft invoice before consultant submission.

- Project Engineering Lead (PEL) / Engineering:

  - Provide MDL

  - Provide Engineering documents

  - Provide official submissions

- Planner:

  - Attend workshop meetings to set material and document issuance schedule.

  - Send Approved required documents to technical office to Create Initial MTS.

  - Send delivery note to TO Engineer.

  - Update material schedule.

  - Receive MTS updated

- Technical Office Engineer:

  - Attending Kickoff meeting and receiving technical package.

  - Create Initial MTS.

  - Receive and review inputs from construction and QC department such as:

- site progress reports from Construction

- and approved IRs/MIRs from QC for invoice preparation.

  - Create QR

  - Receiving and reviewing the Technical Offer from the Proc. Dep.

  - Submitting the Final Technical Evaluation for each Vendor offer

  - Confirming the shortlisted vendors with the Procurement Dep.

  - Create the PRs on the system

  - Review the Draft PO Documents

  - Review the received documents from Engineering Department

  - Submitting the Official Revisions to the DC Department

  - TO shall confirm that the Official Revisions were submitted to the Consultants / Client

  - Preparing the shop drawings

  - Release the IFC drawings

  - Review the work breakdown structure (WBS)

  - Review that the payment breakdown percentage is clearly defined for any lump-sum items.

  - Review shop drawings, IFC drawings, and MCR to check the availability of material.

  - Prepare and update Material control report.

  - Submit Technical documents to QC Engineer.

  - Issue PRs, SCR.

  - Create SVR and final SVR.

  - Participate in Factory Acceptance Test (FAT) if needed.

  - Fulfill technical data on IMIR.

  - Issue the Subcontractors Quantity Survey (QS) report and invoices.

  - Review MRV & sign.

  - Prepare the drafted client invoice and submit it to the PM Department for review.

  - Submit the finalized invoice to the Client Consultant and obtain the Signed Approval.

  - Review the signed invoice details and officially submit the entry on the ERP system.

  - Issue Client Quantity Survey (QS) reports and Invoices.

  - Review and approve IMR, SCIMR, MSR, SSR, FCR.

  - Fulfill Task No. on IMR.

  - Review monthly material report

  - issue sub inventory transfer request if needed

  - Review Material Aging report

  - Issue material storage extension request

  - Issue sub inventory transfer request

  - Review executed quantities with estimated quantities in QS and Shop drawings

  - Issue investigation report and Subcontractor variation request if needed

  - Prepare Work performed quantity statement.

  - Issue client invoice and submit it to consultant.

  - Prepare client final invoices.

  - Review subcontractor draft invoice.

  - Review and check exception letter.

  - prepare subcontractor final invoice request (SFIR).

  - issue and Review subcontractor final invoice.

  - Submit and approve subcontractor final invoice on ERP system.

  - Review and approve on retention release request.

  - Issue retention release on ERP system

  - Prepare and submit to Client the final as built drawings.

  - Collect Technical Learned lessons.

  - Review and approve technical offers.

  - Get the approval for official submittal transmittals

  - Determine the required quantities on IMR/SCIMR based on the approved shop drawings and IFC and the area of work as per the construction plan.

- Document Controller:

  - Create and update project folder on server and upload all technical documents.

    - Update Master Document List (MDL).

  - Update lessons Learned log.

  - Archive all Project Documents.

  - Focal point between head quarter and site (sending and receiving documents during project life cycle)

  - Receive Official submission from TO engineer with Transmittal (Table containing document name, number, and revision).

  - Receive Shop Drawings and obtain consultant / client approval if required then forward to Site DC / TO.

  - Receive Approved Shop Drawings

  - Receive final Technical Offers (Material Submittal).

  - Receive Official Submission.

  - Receive IFC Drawings

  - Attending the FAT. Receive MCR.

  - Receive Subcontract Variation Request.

  - Receive Accepted FCR.

  - Receive Client Invoices

  - Receive As built drawings

  - Update lessons learned log and archive all project documents.

- Site Manager:

  - Submit the Subcontractor progress reports approved by Project Manager.

  - Submit the Client progress reports approved by Project Manager.

  - Submit the Final Client progress reports approved by Project Manager.

  - Submit Approved IRs and SCIMRs Review and approve breakdown analysis

  - Review and approve Subcontractor invoice.

  - Maybe delegated to sign the exception request for one-time, provided that he must get the approved exception request signed by project manager – related construction sector manager within one working day

- Construction Manager:

  - Issue Filed Change Request (FCR) if needed.

  - Submit monthly execution statement for all preformed quantities.

  - Submit Overtime sheet.

  - Submit execution Methodology.

  - Submit IMIR, IIR and IR.

  - Approve verification report.

  - Approve breakdown analysis.

- Construction Team:

  - Submit the Red marked drawings.

  - Issue Internal Material Request (IMR).

  - Issue Material Site Return Request (MSR).

  - Issue Scrap Site Return Request (SSR).

  - Submit and send signed subcontractor progress report.

- QC Engineer:

  - Prepare and send IIR

- Material Controller:

  - Issue Material Categorization Report (MCR)

  - Provide material reports and assist with MRV, MCR, and storage tracking

  - Prepare and send IMIR.

  - Receive approved Signed updated MRV and approved SSR.

  - Prepare and send material Aging report (Oracle ERP) Receive material storage extension request (Oracle ERP).

# Measurement (KPIs):

- All Projects technical data available on project server.

- Technical office progress variance (Planned vs actual) doesn’t exceed 5%.

- All project activities recorded in as built drawings.

- SCRs are issued matching Project schedule.

- Client invoices and subcontractors’ invoices are issued on due dates.

- All Technical Lessons learned are collected, filed, and distributed properly to the concerned departments.

- Resources:

- Manpower as per Project Org Chart

- MS Office Package

- Revit, AutoCAD

- Hardware (Laptops, Desktops, Internet Connectivity)

- Management System

BOQs: Bill of Quantities

TO: Technical Office

PM: Project Manager

PM: Project Manager

TO: Technical Office

MTS: Material Tracking Sheet

PEL: Project Engineering Lead

Procu.: Procurement

QRs: Quotation requests

PRs: Purchase Requests

PRC: Procurement

PM: Project Manager

DC: Document Controller

QRs: Quotation requests

PR: Purchase Request (on ERP system)

Dep: Department

PO: Purchase Order

TO: Technical Office

ENG: Engineering

SD: Project Sector Director

IFC: Issued for Construction

ITP: Inspection and Testing Plan

FAT: Factory Acceptance Test

PR: Purchase Request

DC: Document Control

MC: Material Control

CT: Construction Team

SVR: Subcontractor variation Request

SVO: Subcontractor variation Order

PO: Purchasing Order

IMIR: Internal Material Inspection Request

MRV: Material Receiving Voucher

MC: Material Control

QC: Quality Control

IMR: Internal Material Request

SCMIR: Subcontractor Internal Material Request/Issuance

MSR: Material Site Return.

SSR: Site Scrap Return

MSR: Material Site Return

IIR: Internal Inspection Request.

IR: Inspection Request.

SVR: Subcontractor Variation Request

IIR: Internal Inspection Request.

IR: Inspection Request.

CT: Construction Team

FCR: Field Change Request

IIR: Internal Inspection Request

SCIMR: Subcontractor Internal Material Request

TOAC: Takeover Acceptance Certificate

SCIMR: Subcontractor Internal Material Request

SFIR: Subcontractor Final Invoice Request